## Slide 1
ZYCUS
Programme Health Report
July 2026
Prepared for Executive Leadership
A
Outokumpu S2P
G
UniSan S2P
Confidential | 10 Jul 2026

## Slide 2
Cross-Project Health & Naive Baseline
Snapshot: July 2026
🟡 Outokumpu S2P
Score: 0.37/1.00 P(on-time): 76%
🟢 UniSan S2P
Score: 0.04/1.00 P(on-time) DAG: 7% | v1: 4%
Portfolio avg score: 0.20/1.00 — 0/2 project(s) Red. Monte Carlo P(on-time) accounts for task velocity and variance — not just % complete. See Slide 4 for model comparison.

## Slide 3
Emerging Risks & Root-Cause Analysis
🟡 Outokumpu S2P — AMBER: 54 active at-risk tasks, 60 Red. Top cluster: 28 tasks under abhilasha.s@zycus.com. 76% P(on-time).
🟢 UniSan S2P — GREEN: 51 active at-risk tasks, 42 Red. Top cluster: 26 tasks under UniSan Integration Team. 4% P(on-time).
ℹ️ No projects currently Red. Continue monitoring Amber items and critical-path tasks.
Risk Concentration by Project
Project
At-Risk Active
Top Owner / Cluster
P(on-time)
Outokumpu S2P
54
28 tasks / abhilasha.s@zycus.com
76%
UniSan S2P
51
26 tasks / UniSan Integration Team
7% (DAG)

## Slide 4
Deadline Probability Forecast
Monte Carlo: 10,000 scenarios per project using historical task duration ratios (actual/planned) from completed tasks. v2 (DAG) propagates durations through predecessor graph — respects sequencing structure.
Outokumpu S2P
Deadline: 2026-12-07
v1 (throughput): 76% | v2 skipped (low predecessor coverage)
P(on time)
76%
P(slip ≤1wk)
6%
P(slip 2wk+)
14%
UniSan S2P
Deadline: 2026-10-09
v1 (throughput): 4% → v2 (DAG): 7% (+3 pp from dependency structure)
P(on time)
4%
P(slip ≤1wk)
3%
P(slip 2wk+)
89%

## Slide 5
Key Findings & Recommendations
🔍 Deadline Risk
Outokumpu S2P is the highest-risk project (score 0.367). P(on-time) 76% (throughput model). Deadline: 2026-12-07.
🔍 Critical Path
Outokumpu S2P: 0/15 PM-flagged CP tasks are Red.
🔍 Critical Path
UniSan S2P: 2/50 PM-flagged CP tasks are Red; graph-computed CP = 50 tasks (74% predecessor coverage).
Recommended Actions
✅ Outokumpu S2P
Triage 54 active at-risk tasks with abhilasha.s@zycus.com; escalate any CP tasks that are Red or slipping.
✅ UniSan S2P
Triage 51 active at-risk tasks with UniSan Integration Team; escalate any CP tasks that are Red or slipping.
✅ Data Quality
Ensure Predecessors column is populated in MS Project exports to enable dependency-aware simulation on all projects.

## Slide 6
Appendix — Methodology & Data Quality
RAG Score = 0.60 × Forward Risk + 0.40 × Historical Slip. Forward Risk: fraction of critical-path active tasks that are Red (×1.0) or Amber (×0.5). Falls back to all active tasks if critical count <5. Historical Slip: median(|variance_days|) for late completed tasks, normalised against 30-day ceiling. Variance column sign used (verified: 196/199 rows correct). Magnitude treated as unreliable for parent rows. ML Model top features (GBT, verified this run): total_float_days (0.5439), variance_sign_code (0.2716), pct_complete (0.1054). RAG is manually set by PMs — model learns PM judgment patterns, not a formula. Fit/interpret only — 2 projects, no holdout split. Monte Carlo v1: throughput rate (tasks/week) × log-normal duration-ratio distribution. MC v2 (DAG): discrete-event simulation propagating durations topologically through predecessor graph. v2 runs only when predecessor coverage ≥50%; otherwise v1 is sole forecast. Clustering: TF-IDF + KMeans on available fields (Area, Phase, Owner, Task Name). Sparsity-aware: fields missing in >98% of rows excluded; caveat lists actual population %. Data confidence tiers — High: weighted null rate <20%; Medium: 20–45%; Low: >45%. Predecessor coverage weighted 0.4; planned_days + pct_complete 0.3 each.